## Notice to Taxpayers - Template
NOTICE TO TAXPAYERS
Complete details of the Capital Projects plan may be seen by visiting the website of this unit of government at the following address: https://www.warren.k12.in.us/.
Notice is hereby given to taxpayers of M.S.D. WARREN TOWNSHIP that the proper officers of M.S.D. WARREN TOWNSHIP will conduct a public hearing on the year FY2027 proposed Capital Projects Plan pursuant to IC 20-40-18-6. Following the public hearing, the proper officers of M.S.D. WARREN TOWNSHIP may adopt the proposed plan as presented or with revisions.
| Public Hearing Date: | 2026-03-09
| Public Hearing Time: | 18:00
| Public Hearing Place: | 975 N. Post Road, Indianapolis, IN 46219
Taxpayers are invited to attend the meeting for a detailed explanation of the plan and to exercise their rights to be heard on the proposed plan. If the proposed plan is adopted by resolution, the resolution will be submitted to the Department of Local Government Finance as per IC 20-40-18-6(d).

## Capital Acquisition
Pursuant to IC 20-40-18-6, the MSD Warren Township plan contains a listing of all proposed capital expenditures that exceed $10,000 that are expected to be acquired within the three years immediately following the year the plan was adopted.
| Capital Project Plan Adoption Date: | 2026-03-18
| Asset Description* |  | Acquisition Amount
1 | Service Vehicle |  | 60000
2 | Service Vehicle |  | 60000
3 | Service Vehicle |  | 60000
4 | Service Vehicle |  | 60000
5 | Service Vehicle |  | 60000
6 | Service Vehicle |  | 60000
7 | Police Vehicle |  | 45000
8 | Police Vehicle |  | 45000
9 | ENA VOIP |  | 180000
10 | Zayo Dark Fiber |  | 45000
11 | Infrastructure backup and Anomaly detection |  | 75000
12 | LINQ(Update to Alio Software) |  | 200000
13 | Grounds Equipment |  | 20000
14 | Grounds Equipment |  | 20000
15 | Grounds Equipment |  | 20000
16 | Grounds Equipment |  | 20000
17 | Custodial Equipment |  | 15000
18 | Custodial Equipment |  | 15000
19 | Custodial Equipment |  | 15000
20 | Custodial Equipment |  | 15000
21 | Transportation Forklift |  | 45000
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
Note: The description may include a physical description of the asset and/or any applicable make, model, manufacturer, or VIN Number if applicable.
Additional sheets may be added if necessary

## Projects Capital in Nature
Pursant to IC 20-40-18-6, the MSD Warren Township plan contains a listing of all proposed projects that are capital in nature that exceed $10,000 that are expected to begin within the three years immediately following the year the plan was adopted.
| Capital Project Plan Adoption Date: | 2026-03-18
| Project Description* |  | Estimated Start Date | Estimated End Date | Estimated Project Cost
1 | Classroom flooring replacement at Raymond Park |  | 2026-07-01 | 2027-06-30 | 150000
2 | Flooring at MCRC |  | 2026-07-01 | 2027-06-30 | 150000
3 | MCRC Storefront Doors |  | 2026-07-01 | 2027-06-30 | 40000
4 | WCHS Pool Pumps (2) |  | 2027-07-01 | 2028-06-30 | 70000
5 | Vertical lift installation at Renaissance |  | 2026-07-01 | 2027-06-30 | 750000
6 | HVAC at ECC |  | 2027-07-01 | 2028-06-30 | 500000
7 | HVAC at Renaissance |  | 2026-07-01 | 2027-06-30 | 600000
8 | HVAC at MCRC |  | 2028-07-01 | 2029-06-30 | 1500000
9 | Roof Replacement - various campuses |  | 2027-07-01 | 2028-06-30 | 1000000
10 | Roof Replacement at Lakeside |  | 2026-07-01 | 2027-06-30 | 150000
11 | Roof Replacement at WCHS |  | 2026-07-01 | 2027-06-30 | 1500000
12 | Paving and crack-filling at various campuses |  | 2026-07-01 | 2027-06-30 | 1500000
13 | Replace boiler at WCHS |  | 2026-07-01 | 2027-06-30 | 1000000
14 | Replace cooling towers at WCHS |  | 2026-07-01 | 2027-06-30 | 1750000
15 | Migrate building controls platform at various campuses |  | 2026-07-01 | 2027-06-30 | 3000000
17 | Boiler & Pumps at Lakeside |  | 2026-07-01 | 2027-06-30 | 600000
19 | Boiler & Pumps at Raymond Park |  | 2026-07-01 | 2028-06-30 | 1500000
20 | Domestic Water Heater at Early Childhood |  | 2026-07-01 | 2027-06-30 | 80000
21 | Domestic Water Heater at Highlander Park/WOA |  | 2026-07-01 | 2027-06-30 | 50000
22 | Domestic Water Heater at MCRC |  | 2026-07-01 | 2027-07-01 | 50000
23 | Domestic Water Heater at Stonybrook |  | 2027-07-01 | 2028-06-30 | 65000
24 | Generator at WCHS |  | 2025-07-01 | 2026-06-30 | 500000
25 | Generator at Highlander Park/WOA |  | 2026-07-01 | 2027-06-30 | 100000
26 | Generator at Renaissance |  | 2026-07-01 | 2027-06-30 | 100000
27 | Generator at MCRC |  | 2027-07-01 | 2028-07-01 | 100000
28 | Generator at Stonybrook |  | 2027-07-01 | 2028-07-01 | 100000
29 | Generator at Raymond Park |  | 2027-07-01 | 2028-07-01 | 100000
30 | Sunny Heights Playground Equipment |  | 2026-07-01 | 2027-06-30 | 300000
31 | Roofing at Raymond Park |  | 2027-07-01 | 2028-06-30 | 1500000
33 | Roofing at Liberty Park |  | 2027-07-01 | 2028-06-30 | 500000
34 | Paving at Early Childhood |  | 2027-07-01 | 2028-06-30 | 250000
35 | Paving at Renaissance |  | 2026-07-01 | 2027-06-30 | 250000
36 | Paving at Highlander Park/WOA |  | 2027-07-01 | 2028-06-30 | 250000
37 | Bus Wash at Porter Service Building |  | 2028-07-01 | 2029-06-30 | 225000
38 | Fire & Intercom Upgrades at Renaissance |  | 2028-07-01 | 2029-06-30 | 200000
39 | Fire & Intercom Upgrades at Lakeside |  | 2026-07-01 | 2027-06-30 | 200000
40 | Fire & Intercom Upgrades at Highlander Park/WOA |  | 2027-07-01 | 2028-06-30 | 200000
41 | Fire & Intercom Upgrades at Liberty Park |  | 2027-07-01 | 2028-06-30 | 200000
42 | Electrical/Auto Lighting Switches at Lakeside |  | 2027-07-01 | 2028-06-30 | 100000
43 | Electrical/Auto Lighting Switches at Liberty Park |  | 2026-07-01 | 2027-06-30 | 100000
44 | Electrical/Auto Lighting Switches at Brookview |  | 2027-07-01 | 2028-06-30 | 100000
45 | WCHS Air Handlers - Science Wing |  | 2027-07-01 | 2028-06-30 | 125000
46 | Electrical/Auto Lighting Switches at Early Childhood |  | 2026-07-01 | 2027-06-30 | 100000
Note: Project Description may include a description of the project including physical location, scope of work, and/or internal project name or tracking number.
Additional sheets may be added if necessary

## CP Resolution Template
RESOLUTION TO ADOPT THE CAPITAL PROJECTS FUND PLAN Fiscal Year 2027
This resolution is adopted by the Board of Trustees of the School Corporation below:
| School Corporation Name: | MSD Warren Township
| County: | Marion
WHEREAS, A Capital Project Plan has been established; and
WHEREAS, the Board of Trustees is required under IC 20-40-18-6 to adopt a plan for the Capital Project Plan; and
WHEREAS, the Board of Trustees held a public hearing on the plan date and place below:
| Meeting Date: | 2026-03-09
| Meeting Location: | 975 N. Post Road, Indianapolis, IN 46219
THEREFORE, BE IT RESOLVED, by the Board of Trustees that the plan entitled "FY2025 Capital Project Plan" this resolution, and is adopted as the Board of Trustees' Plan with respect to the Capital Project Plan.
BE IT FURTHER RESOLVED, that the Board of Trustees shall submit a certified copy of this resolution to the Department of Local Government Finance as required by IC 20-40-18-6.
| Adoption Date: | 2026-03-24
| AYE |  | NAY
| Attest: |  | Secretary of Board of School Trustees